## Sheet1
Checklist: Upgrading Hopp from release 2.4 to 2.5
Orchestration
Deploy Hopp.Automation PowerShell module | FALSE | Deploy the Hopp.Automation PowerShell module where used by any orchestration (OPC, Octopus Deploy, Control-M, DevOps or others) Copy the Hopp.Automation folder from the download to C:\Program Files\WindowsPowerShell\Modules (remove the Hopp.Automation folder first if present from earlier installation)
Refresh Database setup scripts | FALSE | If you have automated procedures to create new tracks, databases and more in the Hopp environment, refresh the MigFx.*Db.Setup.sql database setup scripts from the download page
Database
Backup all Migration databases | FALSE | Backup all Migration_* databases on all execution servers
Backup Repository database | FALSE
Run MigrationDb refactor script | FALSE | Run MigrationDb refactor script on all Migration_* databases on all execution servers
Backup Master database | FALSE
Run MasterDb refactor script | FALSE | Run the MasterDb refactor script from the release notes in the Master database
Master Server
Redeploy the Hopp Portal | FALSE | Stop the Portal App Pool
| FALSE | Preserve the existing appsettings.json file
| FALSE | The wwwroot/index.html file has changed in this release. If hosting the Portal in a sub-folder under IIS: Open the wwwroot/index.html file and note down the value of the <base> tag in the beginning of the file in order to be able to restore it later
| FALSE | If you are using the Planning and Item Manager extensions: Redeploy from the PortalWithModules.zip file Otherwise: Redeploy from the Portal.zip file
| FALSE | Restore the appsettings.json file. There are no changes to the file in this release
| FALSE | If hosting the Portal in a sub-folder under IIS: Open the wwwroot/index.html file and restore the <base> tag that was noted down above
| FALSE | Start the Portal App Pool
All Execution Servers
Reinstall the Hopp Agent Service | FALSE | Make sure you have the credentials for the Hopp application account available
| FALSE | Stop all tracks on the Server (from Portal or from Task Manager)
| FALSE | Stop the Agent service before uninstall
| FALSE | Preserve the MigFx.Agent.dll.config file from installation location (normally C:\Program Files\HoppTech\migFx\Agent) before uninstall
| FALSE | Install the Agent service from the download page
| FALSE | Restore the MigFx.Agent.dll.config file. There are no changes to the file in this release
| FALSE | Re-enter the Hopp application account as logon credentials for the Agent service
| FALSE | Start the Agent Service
Reinstall DataServices | FALSE | If installed: Reinstall Hopp.DataServices.SqlServer
| FALSE | If installed: Reinstall Hopp.DataServices.DB2
| FALSE | If installed: Reinstall Hopp.DataServices.Oracle
Workstations
Reinstall Hopp Studio | FALSE | No need to uninstall first
Run refactor on Studio Maps | FALSE | After reinstall of Studio, run refactor as per release notes
Reinstall DataServices | FALSE | If installed: Reinstall Hopp.DataServices.SqlServer
| FALSE | If installed: Reinstall Hopp.DataServices.DB2
| FALSE | If installed: Reinstall Hopp.DataServices.Oracle
Reinstall Hopp.Automation PowerShell module (if installed) | FALSE | Copy the Hopp.Automation folder from the download to C:\Program Files\WindowsPowerShell\Modules (remove the Hopp.Auotmaition folder first if present from earlier installation)
Update Visual Studio 2022 | FALSE | Update Visual Studio 2022 to minimum version 17.14
Reinstall the Hopp Visual Studio extension | FALSE | Open Visual Studio and mark the Hopp Migration extension for uninstall
| FALSE | Close Visual Studio and allow the VSIX installer to uninstall the extension
| FALSE | Install new Hopp.VsExtension.2022.vsix
Upgrade general NuGet references | FALSE | Upgrade all *.SourceEngineGenerated, *.TargetEngine projects and any projects for custom implementations of Hopp extensions • Microsoft.EntityFrameworkCore.SqlServer package reference to 8.0.17 • Microsoft.Data.SqlClient package reference to 5.2.3
If using Hopp Libraries from NuGet
Upgrade Hopp NuGet references | FALSE | Update all Hopp.* package references to 2.5.* • All *.SourceEngineGenerated, *.TargetEngine projects • Any projects for custom implementations of Hopp extensions
Update Generator tool (Only if using Hopp libraries from NuGet) | FALSE | Run dotnet tool update Hopp.Tools.EngineGenerator --global from a commend prompt
If not using Hopp Libraries from NuGet
Reinstall Hopp.EngineGenerator | FALSE | No need to uninstall first
Reinstall Hopp.Libraries | FALSE | No need to uninstall first
Release-specific refactoring
Decommission Reformatters | FALSE | Replace any custom reformatter implementations with new BulkDataProvider implementations provided by Hopp
Refactor Audit | FALSE | If custom Audit Collection and Result extensions are implemented, refactor as per release notes
Refactor Extension constructors | FALSE | If any custom extensions are implemented for the Hopp Runtime (for instance Target Unload), refactor as per release notes
Portal configurations
DB2 unload files | FALSE | In the Portal Operations, any files received from DB2 that were previous loaded using the DB2 reformatter provided by Hopp must now be changed to use the new RFC4180 compliant Csv BulkDataProvider. Configure the new RFC4180 to use semi-colon as field delimiter and a # character as quote character
Upload new Runtime | FALSE | Upload the runtime.zip to the Portal configuration
Before running any jobs | FALSE | Redeploy Source- and Target Enginesengines • Studio validation • Studio publish • Visual Studio generation • Visual Studio deploy
| FALSE | Restart Track
| FALSE | Run setup of Source- and Target Engine